## Sheet1
Tasks | Estimated hours | Sprint 1 hours | Sprint 2 hours | Sprint 3 hours | Sprint 4 hours | Sprint 5 hours | Sprint 6 hours | Sprint 7 hours | Sprint 8 hours | Sprint 9 hours | Sprint 10 hours | Sprint 11 hours | Sprint 12 hours | Sprint 13 hours | Sprint 14 hours | Sprint 15 hours | Sprint 16 hours | Total hours | Column1
idea | 100 | 40 | 40 | [14 empty] | 90
choosing an idea | 5 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 20
project description | 10 | 0 | 0 | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 20
setting scrum envirn. | 10 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 3
prooject desciption | 8 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 10
users stories | 50 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 5
requiment | 20 |  |  |  | 7 | [12 empty] | 7
fead back on the p | 5 |  |  |  | 0 | 5 | [11 empty] | 5
use case | 20 |  |  |  |  | 20 | [11 empty] | 20
use case description | 20 |  |  |  |  | 20 | 12 | [10 empty] | 32
project report | 80 | [5 empty] | 5 |  |  |  | 10 | 2 | 5 | 10 | 10 | 10 | 29 | 81
sequence diagram | 20 | [6 empty] | 6 |  |  |  | 2 | [5 empty] | 8
Architictur diagram | 10 | [6 empty] | 6 | [9 empty] | 6
conceptual diagram | 20 | [6 empty] | 6 | [9 empty] | 6
Scenarios | 25 | [6 empty] | 7 | [9 empty] | 7
Process report | 30 | [6 empty] | 6 | [5 empty] | 20 |  |  |  | 26
class diagram | 40 | [7 empty] | 5 |  |  | 2 | 5 |  |  |  |  | 12
conceptual diagram | 10 | [7 empty] | 5 | [8 empty] | 5
data base modeling | 80 | [7 empty] | 20 |  |  |  | 10 |  |  |  |  | 30
model imp. | 100 | [7 empty] | 40 | [8 empty] | 40
move code factura. | 10 | [8 empty] | 2 | [7 empty] | 2
user code factura. | 10 | [8 empty] | 2 | [7 empty] | 2
ticket code factura. | 10 | [8 empty] | 2 | [7 empty] | 2
user imp. c# | 10 | [9 empty] | 10 | [6 empty] | 10
movie imp. C# | 10 | [9 empty] | 10 | [6 empty] | 10
ticket imp. C# | 10 | [9 empty] | 10 | [6 empty] | 10
data base con. | 40 | [9 empty] | 20 | [6 empty] | 20
Client GUI | 40 | [9 empty] | 50 | [6 empty] | 50
implementation | 40 | [10 empty] | 41 | [5 empty] | 41
testing | 20 | [10 empty] | 10 | 17 | 20 | 20 | 10 | 8 | 85
security planing | 20 | [10 empty] | 10 | [5 empty] | 10
scrum doc. | 10 | [11 empty] | 15 |  |  |  |  | 15
implementation | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 20 |  | 0 | 21
Github doc. | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | 0 | 1
implementation | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 3 | 11 | 10 |  | 0 | 56
Cantt chart | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 2 | 0 | 10 |  | 0 | 28
implementation | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 37 |  |  | 20 | 10 | 97
burndown chart | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 |  | 10 | 8 | 28
user manual | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 20 | 20
Actual remaining hours | 1140 | 1140 | 1090 | 1060 | 1020 | 975 | 948 | 917 | 839 | 840 | 800 | 800 | 700 | 680 | 620 | 600 | 0
Estimated hours | 1140 | 1120 | 1080 | 1040 | 1000 | 960 | 920 | 880 | 840 | 800 | 760 | 720 | 680 | 640 | 600 | 560 | 0